## Sheet1
Doc | Area / Gap | Owner | Deliverable | Purpose (What Gap It Solves) | Proposal | Speaker Notes
Integration Layer | Protocol Contract Definition | Lead Engineer | JSON schemas, message envelopes, versioning rules | Removes ambiguity in tool integrations; future UI/tool migrations become seamless | Establish a protocol-first approach with strict schema validation + centralized schema registry | As noted, Removes ambiguity in tool integrations; future UI/tool migrations become seamless. Proposed approach: Establish a protocol-first approach with strict schema validation + centralized schema registry
Integration Layer | Workflow Error & Retry Model | Architect (You) | End-to-end retry logic, rollback plan, DLQ handling, idempotency rules | Ensures reliability, consistency, safe recovery under load | Implement 3-tier retry (transient, workflow, system), transaction IDs, workflow checkpoints | As noted, Ensures reliability, consistency, safe recovery under load. Proposed approach: Implement 3-tier retry (transient, workflow, system), transaction IDs, workflow checkpoints
Integration Layer | Sequence / Data Flow Diagrams | Solution Engineer | Request/response diagrams + retry/failure flows | Clarifies orchestration lifecycle; reduces confusion during reviews | Create swimlane diagrams showing ingestion → orchestration → adapter → Databricks paths | As noted, Clarifies orchestration lifecycle; reduces confusion during reviews. Proposed approach: Create swimlane diagrams showing ingestion → orchestration → adapter → Databricks paths
Integration Layer | Observability Blueprint | DevOps | Logging structure, tracing strategy, dashboards, alerts | Fills the visibility gap; supports SLA/SLO compliance | Use App Insights + Log Analytics + correlation IDs + automated alert routes | As noted, Fills the visibility gap; supports SLA/SLO compliance. Proposed approach: Use App Insights + Log Analytics + correlation IDs + automated alert routes
Integration Layer | Adapter Interface Design | Each Sub-Team (PowerApps, SharePoint, Dataverse, Databricks) | API/interface definition, transformation logic | Decouples systems; avoids tool-specific logic in workflows | Use adapter microservices with standardized protocol translation + versioned APIs | As noted, Decouples systems; avoids tool-specific logic in workflows. Proposed approach: Use adapter microservices with standardized protocol translation + versioned APIs
Integration Layer | Databricks Integration Contract | Data Engineering | Bronze/Silver/Gold structure, validation rules, schema evolution | Clarifies handoff responsibilities and downstream data quality | Adopt Delta Live Tables or structured pipelines with schema enforcement and metadata contracts | As noted, Clarifies handoff responsibilities and downstream data quality. Proposed approach: Adopt Delta Live Tables or structured pipelines with schema enforcement and metadata contracts
Integration Layer | Security & Compliance Pack | Cloud/Security | IAM roles, secrets management, encryption, audit logging | Closes governance, RBAC, and audit gaps | Enforce managed identities, key rotation, private endpoints, full audit trails | As noted, Closes governance, RBAC, and audit gaps. Proposed approach: Enforce managed identities, key rotation, private endpoints, full audit trails
Integration Layer | Performance & Scalability Modeling | Architect + DevOps | Throughput targets, concurrency models, load testing plan | Answers capacity/performance questions; validates enterprise scale | Simulate peak ingestion → queue depth → Durable Functions concurrency → Databricks load | As noted, Answers capacity/performance questions; validates enterprise scale. Proposed approach: Simulate peak ingestion → queue depth → Durable Functions concurrency → Databricks load
Integration Layer | UI Migration Readiness | App Team + Architect | Protocol-only UI dependency strategy | Ensures system isn't tied to PowerApps or SharePoint | Upstream tools become “clients” of the protocol; only adapters change during UI migration | As noted, Ensures system isn't tied to PowerApps or SharePoint. Proposed approach: Upstream tools become “clients” of the protocol; only adapters change during UI migration
Integration Layer | Operational Runbook | Platform Ops | Deployment steps, rollback, reprocessing, on-call SOPs | Prevents operational failures and support delays | Create runbooks for failures, reruns, DLQ processing, adapter restarts, observability use | As noted, Prevents operational failures and support delays. Proposed approach: Create runbooks for failures, reruns, DLQ processing, adapter restarts, observability use
Agentic AI Solution | Missing end-to-end architecture diagram | AI Engineering / Architecture | System Architecture Diagram (Data Flow + LangGraph Flow + API exposure) | Provides clarity on interaction between parsing, scoping, matching, evaluation, and services; eliminates ambiguity in control flow. | Create a single blueprint-style diagram consolidating all agents, state transitions, API boundaries, and logging checkpoints. Use this as the authoritative reference for dev and audit teams. | As noted, Provides clarity on interaction between parsing, scoping, matching, evaluation, and services; eliminates ambiguity in control flow.. Proposed approach: Create a single blueprint-style diagram consolidating all agents, state transitions, API boundaries, and logging checkpoints. Use this as the authoritative reference for dev and audit teams.
Agentic AI Solution | Scoping rules not fully defined | SME + AI Engineering | Scoping Validation Contract | Ensures consistent behavior when metadata is incomplete or missing; prevents unsafe scoping outcomes. | Define explicit minimum metadata, introduce a “scoping reject” state, and add optional user overrides with audit logging. | As noted, Ensures consistent behavior when metadata is incomplete or missing; prevents unsafe scoping outcomes.. Proposed approach: Define explicit minimum metadata, introduce a “scoping reject” state, and add optional user overrides with audit logging.
Agentic AI Solution | Configuration governance not documented | Architecture + Product Owner | Configuration Registry Design | Prevents unauthorized method/prompt changes; establishes versioning and auditability. | Stand up a lightweight configuration registry (e.g., JSON-based with versioned entries) with an approval workflow and drift-detection alerts. | As noted, Prevents unauthorized method/prompt changes; establishes versioning and auditability.. Proposed approach: Stand up a lightweight configuration registry (e.g., JSON-based with versioned entries) with an approval workflow and drift-detection alerts.
Agentic AI Solution | User Confirmation workflow not detailed | Product + UX | User Confirmation Flow | Ensures users clearly understand selected methods/prompts and provides traceable acceptance/override logs. | Implement a confirmation modal or step that displays the selected method, metadata, allowed overrides, and captures justification + timestamp. | As noted, Ensures users clearly understand selected methods/prompts and provides traceable acceptance/override logs.. Proposed approach: Implement a confirmation modal or step that displays the selected method, metadata, allowed overrides, and captures justification + timestamp.
Agentic AI Solution | No structured error-handling model | AI Engineering | Error Handling Framework | Improves reliability, debugging efficiency, and consistent behavior across agents. | Introduce standardized agent-level error codes, explicit retry logic for transient failures, and a “halt + notify” mechanism for deterministic blockers. | As noted, Improves reliability, debugging efficiency, and consistent behavior across agents.. Proposed approach: Introduce standardized agent-level error codes, explicit retry logic for transient failures, and a “halt + notify” mechanism for deterministic blockers.
Agentic AI Solution | No performance/scalability guidelines | Architecture + DevOps | Performance Benchmark Plan | Ensures system performs consistently during high-volume multi-lab usage. | Define latency budgets per agent, load-test LangGraph orchestration, and document horizontal scaling patterns for the Node.js service. | As noted, Ensures system performs consistently during high-volume multi-lab usage.. Proposed approach: Define latency budgets per agent, load-test LangGraph orchestration, and document horizontal scaling patterns for the Node.js service.
Agentic AI Solution | No audit logging & retention strategy | Security + Architecture | Audit Logging Standard | Provides traceability for governance, compliance, and replayability. | Create a required audit schema (e.g., config version, user ID, timestamps), enforce through middleware, and align retention with compliance rules. | As noted, Provides traceability for governance, compliance, and replayability.. Proposed approach: Create a required audit schema (e.g., config version, user ID, timestamps), enforce through middleware, and align retention with compliance rules.
Agentic AI Solution | No sandbox/testing strategy for new prompts/methods | AI Engineering + QA | Prompt/Method Sandbox | Reduces risk by allowing controlled testing before production adoption. | Build a non-production evaluation environment where new prompts/methods can be validated using known datasets and SMEs can sign off. | As noted, Reduces risk by allowing controlled testing before production adoption.. Proposed approach: Build a non-production evaluation environment where new prompts/methods can be validated using known datasets and SMEs can sign off.
Agentic AI Solution | Undefined ownership of method/prompt catalog | Product Owner | RACI Matrix for Configuration Ownership | Ensures clear governance for updating and approving method/prompt entries. | Assign SMEs as approvers, AI engineers as implementers, and product as the curator; publish RACI and add to onboarding docs. | As noted, Ensures clear governance for updating and approving method/prompt entries.. Proposed approach: Assign SMEs as approvers, AI engineers as implementers, and product as the curator; publish RACI and add to onboarding docs.
Agentic AI Solution | No deterministic replay strategy | AI Engineering | Evaluation Replay Specification | Enables audit replay, compliance checks, and reproducibility. | Capture evaluation inputs, config versions, and log seeds where applicable to allow deterministic re-run of any evaluation event. | As noted, Enables audit replay, compliance checks, and reproducibility.. Proposed approach: Capture evaluation inputs, config versions, and log seeds where applicable to allow deterministic re-run of any evaluation event.
Agentic AI Solution | Cross-lab scaling strategy unclear | Architecture | Multi-Lab Deployment Model | Ensures consistent deployment across labs while respecting data boundaries. | Define whether each lab gets isolated configuration namespaces or shared with overrides; document replication and governance model. | As noted, Ensures consistent deployment across labs while respecting data boundaries.. Proposed approach: Define whether each lab gets isolated configuration namespaces or shared with overrides; document replication and governance model.
Agentic AI Solution | Minimal metadata contract between parsing → scoping not defined | Parsing Team + AI Team | Metadata Contract Specification | Prevents downstream failure and ambiguity in matching/evaluation. | Create a schema defining mandatory fields, optional metadata, and fallback logic; enforce via schema validation before scoping. | As noted, Prevents downstream failure and ambiguity in matching/evaluation.. Proposed approach: Create a schema defining mandatory fields, optional metadata, and fallback logic; enforce via schema validation before scoping.
Foundation Platform | 1. SLA, RPO/RTO Not Defined | Architecture + Infra | SLA & DR Strategy Document | Clarifies system guarantees for uptime, failover, recovery; reduces ambiguity during audits | Define API response times, orchestrator processing thresholds, RPO < 15 min, RTO < 1 hr; document Postgres HA, storage redundancy | As noted, Clarifies system guarantees for uptime, failover, recovery; reduces ambiguity during audits. Proposed approach: Define API response times, orchestrator processing thresholds, RPO < 15 min, RTO < 1 hr; document Postgres HA, storage redundancy
Foundation Platform | 2. No clear decision framework for When to Use Power Apps vs New Azure Stack | Architecture + Product | Decision Matrix & Flowchart | Helps teams decide which workflows stay on PowerApps vs migrate; avoids rework | Create criteria matrix: CRUD/simple → PowerApps; High-volume AI/agentic flows → Azure | As noted, Helps teams decide which workflows stay on PowerApps vs migrate; avoids rework. Proposed approach: Create criteria matrix: CRUD/simple → PowerApps; High-volume AI/agentic flows → Azure
Foundation Platform | 3. AI Prompt Governance Model Missing | AI Lead + Architecture | Prompt Registry & Versioning Framework | Ensures auditability, rollback, consistency across labs; required for compliance | Implement structured prompt table in Postgres + version tags + approval workflow + rollback | As noted, Ensures auditability, rollback, consistency across labs; required for compliance. Proposed approach: Implement structured prompt table in Postgres + version tags + approval workflow + rollback
Foundation Platform | 4. Cost Governance for AI Not Fully Defined | Product + Architecture + Finance | AI Cost Governance Playbook | Prevents AI cost overruns; provides predictable budgeting | Set token budgets per workflow/lab; implement dashboards tagging LLM calls; alerts on spikes | As noted, Prevents AI cost overruns; provides predictable budgeting. Proposed approach: Set token budgets per workflow/lab; implement dashboards tagging LLM calls; alerts on spikes
Foundation Platform | 5. Observability Strategy Strong but Missing Incident Playbooks | SRE / DevOps | Operational Runbooks & Incident Response Guide | Ensures repeatable triage, reduces MTTR, clarifies escalation paths | Create playbooks for queue backlog, LLM failures, Postgres latency, container crashes | As noted, Ensures repeatable triage, reduces MTTR, clarifies escalation paths. Proposed approach: Create playbooks for queue backlog, LLM failures, Postgres latency, container crashes
Foundation Platform | 6. No Load/Performance Testing Plan | QA Perf + Architecture | Performance Testing Plan | Validates scalability target of ~500k submissions/year | Simulate submission spikes, test orchestrator autoscale, test Service Bus backlog clearing | As noted, Validates scalability target of ~500k submissions/year. Proposed approach: Simulate submission spikes, test orchestrator autoscale, test Service Bus backlog clearing
Foundation Platform | 7. Migration Strategy Good but Missing Data Reconciliation Steps | Data Engineering | Migration Validation Checklist | Ensures confidence in early pilots; avoids “trust issues” with new system | Add checks: record counts, metadata consistency, error logs, AI output divergences | As noted, Ensures confidence in early pilots; avoids “trust issues” with new system. Proposed approach: Add checks: record counts, metadata consistency, error logs, AI output divergences
Foundation Platform | 8. Integration with Existing Databricks Workflows Not Operationalized | Data Eng + Analytics | Integration Contract & Sync Process | Ensures data consistency between OLTP (Postgres) and Lakehouse; supports analytics | Define cadence of delta loads into ADLS; implement export microservice or structured ETL job | As noted, Ensures data consistency between OLTP (Postgres) and Lakehouse; supports analytics. Proposed approach: Define cadence of delta loads into ADLS; implement export microservice or structured ETL job
Foundation Platform | 9. User Roles & RBAC Model Under Defined | Architecture + Security | RBAC Matrix & Policy Doc | Eliminates ambiguity: which roles read, write, manage prompts, access AI logs | Map Azure AD groups → Application roles; implement NestJS guards + row-level checks | As noted, Eliminates ambiguity: which roles read, write, manage prompts, access AI logs. Proposed approach: Map Azure AD groups → Application roles; implement NestJS guards + row-level checks
Foundation Platform | 10. No End-to-End Architecture Sequence Diagrams | Architecture | Sequence Diagram Pack | Communicates orchestration clearly; helps in audits and onboarding | Add diagrams for submission flow, AI orchestrator flow, error-handling path, analytics sync | As noted, Communicates orchestration clearly; helps in audits and onboarding. Proposed approach: Add diagrams for submission flow, AI orchestrator flow, error-handling path, analytics sync
Foundation Platform | 11. API Contracts Not Fully Finalized (OpenAPI Defined, But Not Complete) | Backend Lead | API Contract (OpenAPI 3.0) | Enables integration teams, reduces development friction |  | As noted, Enables integration teams, reduces development friction. Proposed approach: nan
Desinger Prompt | Detailed ERD/schema not documented | Engineering (Ragip) + Architect | Full ERD + Data Dictionary | Ensures dev team has clear blueprint; removes ambiguity around constraints, relationships, indexes | Create v1 ERD + validation rules; schedule schema review with SMEs & Orchestrator team | As noted, Ensures dev team has clear blueprint; removes ambiguity around constraints, relationships, indexes. Proposed approach: Create v1 ERD + validation rules; schedule schema review with SMEs & Orchestrator team
Desinger Prompt | Prompt Set mechanism introduced, but lifecycle/“release” concept not defined | Architect + Product Owner | Prompt Set Release Model + Versioning Rules | Prevents accidental production changes and ensures reproducibility | Introduce PromptSetRelease entity; every change creates new release, existing releases immutable | As noted, Prevents accidental production changes and ensures reproducibility. Proposed approach: Introduce PromptSetRelease entity; every change creates new release, existing releases immutable
Desinger Prompt | Draft → Active → Deprecated workflow is conceptual only; no operational details | SMEs + Product Owner | SOP for Prompt Lifecycle | Gives SMEs clear, safe workflow; eliminates misconfiguration | Document step-by-step lifecycle; include approval workflow, constraints, auto-validation | As noted, Gives SMEs clear, safe workflow; eliminates misconfiguration. Proposed approach: Document step-by-step lifecycle; include approval workflow, constraints, auto-validation
Desinger Prompt | Roles (SME, Admin, Viewer) not defined with actions and boundaries | Architect | RBAC Matrix | Prevents unauthorized changes and ensures audit readiness | Define role → action mappings (create, activate, deprecate, attach-to-set); enforce via middleware | As noted, Prevents unauthorized changes and ensures audit readiness. Proposed approach: Define role → action mappings (create, activate, deprecate, attach-to-set); enforce via middleware
Desinger Prompt | AI agent proposal flow is loosely defined | AI Team + Architect | Agent-to-SME Approval Workflow | Ensures agents cannot auto-activate prompts; maintains human oversight | Require all AI-generated prompts to enter draft state with provenance metadata and SME approval gate | As noted, Ensures agents cannot auto-activate prompts; maintains human oversight. Proposed approach: Require all AI-generated prompts to enter draft state with provenance metadata and SME approval gate
Desinger Prompt | PromptRun model defined but no strategy for snapshot storage | Engineering | PromptRun Audit Strategy | Ensures “why did this flag fire?” questions can always be answered | Store exact version FK + optional prompt snapshot; include hash of effective prompt text | As noted, Ensures “why did this flag fire?” questions can always be answered. Proposed approach: Store exact version FK + optional prompt snapshot; include hash of effective prompt text
Desinger Prompt | JSONB metadata defined but no schema validation rules | Engineering | Metadata Validation Framework | Prevents runtime failures due to malformed metadata | JSON schema validation on insert/update; unit tests for run condition rules | As noted, Prevents runtime failures due to malformed metadata. Proposed approach: JSON schema validation on insert/update; unit tests for run condition rules
Desinger Prompt | No sizing, retention, or archive strategy | Architect + Engineering | Data Growth & Archive Plan | Ensures long-term sustainability and predictable DB growth | Archive deprecated versions >12 months; move large prompt bodies to S3 if needed | As noted, Ensures long-term sustainability and predictable DB growth. Proposed approach: Archive deprecated versions >12 months; move large prompt bodies to S3 if needed
Desinger Prompt | How UI/Orchestrator selects versions is not standardized | Orchestrator Team | API Contract for Prompt Fetch | Prevents inconsistencies between UI, backend, and runtime execution | Standardize API: GET prompt/{id}/active; Orchestrator logs version used during run | As noted, Prevents inconsistencies between UI, backend, and runtime execution. Proposed approach: Standardize API: GET prompt/{id}/active; Orchestrator logs version used during run
Desinger Prompt | No mention of prompt unit tests, regression tests, or version comparison tests | QA + Engineering | Prompt Test Framework | Ensures changes don’t break logic or cause prompt regressions | Add test modules: version diff tests, metadata regression tests, prompt set integrity tests | As noted, Ensures changes don’t break logic or cause prompt regressions. Proposed approach: Add test modules: version diff tests, metadata regression tests, prompt set integrity tests
Desinger Prompt | Existing prompts need a migration plan into versioned model | Engineering + SMEs | Migration Playbook | Prevents data loss or mismatches when transitioning to v1 | Script to create Prompt + initial PromptVersion; tag with SME owner & display group | As noted, Prevents data loss or mismatches when transitioning to v1. Proposed approach: Script to create Prompt + initial PromptVersion; tag with SME owner & display group
Desinger Prompt | Wrong versions could be added to Prompt Sets | Engineering | Pre-deployment Validation | Protects production from human error | Add validation: only active versions can be attached; warn if older version in use | As noted, Protects production from human error. Proposed approach: Add validation: only active versions can be attached; warn if older version in use
Desinger Prompt | UI/UX implications not documented (filtering, comparison, history view) | UX + SMEs | UI Mockups | Makes versioning manageable for non-technical SMEs | Build version history UI with diff viewer; filters by owner/status/display group | As noted, Makes versioning manageable for non-technical SMEs. Proposed approach: Build version history UI with diff viewer; filters by owner/status/display group
Desinger Prompt | No defined “prompt release cycle” for production | Product Owner | Release Governance Model | Provides predictability and reduces fire-drill changes | Adopt monthly release cadence; emergency changes require architect approval | As noted, Provides predictability and reduces fire-drill changes. Proposed approach: Adopt monthly release cadence; emergency changes require architect approval
Desinger Prompt | No mapping to regulatory requirements (traceability, audit trail) | Architect + Compliance | Compliance Checklist | Ensures model satisfies future regulatory asks | Map design to CFR 21 Part 11, audit trail, traceability, version integrity | As noted, Ensures model satisfies future regulatory asks. Proposed approach: Map design to CFR 21 Part 11, audit trail, traceability, version integrity