## Sheet1
Layer / Component | Description | Service Used | Phase / Month | Key User Stories / Tasks | Outcome | Dependencies & Notes | Speaker Notes (Storytelling Style with Yash Feedback Context)
Preprocessing | Enhance input quality for OCR and layout detection | OpenCV (denoise, deskew), Azure Vision API | Month 1 | Add image cleanup and quality scoring before extraction | Improves OCR accuracy and reduces extractor errors | Needs DI/Textract input sample library | We start right at the source, cleaning up the raw inputs. Using OpenCV and Azure Vision, we can denoise and straighten forms before any extraction. This is new in the framework because it wasn’t part of version 1; it came out of our observation that cleaner input improves extraction accuracy.
Layout Registry | Central registry for infinite layout handling | PostgreSQL or Cosmos DB + pgvector for KNN search | Month 1 | Create registry with embedding fingerprints and metadata | Enables adaptive layout recognition and reuse | Vector DB performance tuning required | This is one of the big new pieces — this layout registry to act like the system’s memory. It would help us recognize previously seen layouts using embeddings, so we don’t start from scratch every time.
Embedding-based Clustering (ADAH) | Clusters similar layouts for reusability | SentenceTransformer or Azure OpenAI embeddings | Month 3 | Add ADAH logic to auto-group layouts and avoid duplicates | Reduces retraining and improves registry efficiency | Needs sample embedding pipeline from AOAI | Here’s where infinite layout handling becomes manageable. This was strengthened after Yash’s feedback so we’re focusing more on generalization rather than expanding registry entries endlessly. In v1, No clustering or adaptive heuristics existed — layout handling is one-to-one, not grouped. Instead of managing infinite layouts individually, ADAH groups similar ones together. It’s like recognizing that different versions of the same form are part of one family.
Arbitration Layer | Compare outputs from multiple extractors | Weighted Confidence Scoring (rule-based ML) | Month 1–2 | Build arbitration logic across Textract, DI, AOAI | Selects best field values and boosts accuracy | Needs output confidence scores from each model | This piece isn’t new — we’re already comparing outputs between multiple extractors. We’re not introducing arbitration rather we’re going to formalize and instrument the existing ‘agreeing model’ with policies, metrics, and a feedback loop so it’s tunable, explainable, and continuously improving.
Multi-Model Extraction | Run ensemble extraction using multiple tools | AWS Textract + Azure DI + AOAI (prompt-based) | Month 1 | Wire extractors to common interface for arbitration | Preserves accuracy, avoids dependency on one cloud | Requires stable DI access & Textract creds | We’re not replacing Textract or Azure OpenAI — we’re keeping both. Yash made it clear that cloud unification isn’t the goal; accuracy is. So we continue using both extractors but orchestrate them more cleanly through an arbitration layer that scores confidence and consistency.
Schema Validation | Validate output structure and logic | JSON Schema + Python Validation Framework | Month 1 | Enforce required fields, data types, null checks | Prevents downstream errors in XML generation | Final schema confirmation from Yash pending | We’ve refined schema validation so it’s stricter but smarter. We still check structure — required fields, types — but now we also validate logical completeness, catching subtle errors that slip through. This helps us ensure consistency without rearchitecting the entire pipeline.
Semantic Validation | Validate drug names, reactions, and AE details | RxNorm API, MedDRA local dataset | Month 3 | Add semantic checks for clinical correctness | Ensures regulatory compliance and improves trust | MedDRA license validation | “Another key addition from the feedback — this layer ensures meaning, not just structure. By validating drug names, reactions, and severity using RxNorm and MedDRA, we align the data with real-world medical terminology. It’s a clinical quality gate before publishing.”
HITL Feedback Loop | Capture human corrections into system | Custom UI (Flask or Streamlit) + DB feedback table | Month 2 | Build lightweight interface for corrections | Continuous learning via human reinforcement | Connects back to registry updates | “We’ve enhanced the human-in-the-loop process so that reviewers’ corrections directly improve the model. Yash specifically emphasized enabling business users to fine-tune models themselves. So this loop will now power client-level fine-tuning without developer intervention.”
Policy Configuration | Define thresholds and routing logic | YAML/JSON Configs + Azure Function | Month 2 | Parameterize thresholds, retry logic, and routing | Allows non-code tuning of model behaviors | Linked to arbitration and schema layer | “We’re making configuration lightweight — all thresholds, retry limits, and routing logic move into simple JSON/YAML configs. This gives teams flexibility to adapt without redeploying code — something leadership highlighted as a scalability requirement.”
Layout Generalization | Merge similar layout clusters | K-Means / DBSCAN or cosine similarity thresholds | Month 3 | Implement auto-merge of similar layouts | Keeps registry clean and scalable | Uses pgvector embeddings for similarity | Registry bloat was one concern Yash raised. So we’re introducing auto-merge logic to combine similar layouts. It’s like decluttering the registry so we learn once, apply many times, and keep it maintainable over time.
DI-Custom Models | Train custom models for high-volume layouts | Azure Document Intelligence (custom projects) | Month 4 | Train DI-Custom for top 10 layouts | Boosts accuracy for premium clients | Requires top layout frequency stats | “Previously, the plan was to move everything to DI-Custom. Based on feedback, we’re narrowing that scope. We’ll train custom models only for top layouts where it brings measurable value — not across the board.”
Client-Specific Fine-Tuning | Enable prompt or model fine-tuning | AOAI Fine-tuning API / Prompt Engineering | Month 5 | Build per-client fine-tuning profiles | Achieves 90%+ accuracy for premium clients | Client selection and cost approval | We’re also adding client-level fine-tuning — but through a self-serve model. Premium clients can now fine-tune their configurations or prompts directly, which helps us meet high-accuracy demands without new dev cycles.
Observability & Metrics | Track performance and drift | App Insights + OpenTelemetry | Ongoing | Implement dashboards (accuracy, latency, drift) | Improves transparency and traceability | Needs telemetry integration per layer | This layer has been expanded to include drift and field-level accuracy tracking. It’s all about transparency — not just if it failed, but why and where. That visibility helps us prove our value back to the business.
Security & Identity | Manage credentials and access | Managed Identity + Key Vault | Ongoing | Replace static keys with managed identities | Strengthens compliance and reduces risk | Azure IAM roles setup needed | We’re maintaining enterprise-grade security by replacing static credentials with Managed Identity and Key Vault. That wasn’t a new ask, but it’s become a non-negotiable foundation as we scale this pipeline.
Publishing & Integration | Generate validated JSON/XML outputs | Python Lambda / Azure Function | Month 5 | Add publishing to downstream XML service | Ensures traceable, FDA-ready output | Awaiting XML schema from TFS | Once everything passes validation, the data gets packaged as JSON or XML and handed off downstream. This stays mostly the same but now includes traceable lineage tags for audit and FDA submission readiness.
Continuous Improvement Loop | Feed back schema or layout changes | Registry updates via Cron/Function | Ongoing | Automate registry refresh with new layouts | Maintains continuous learning and accuracy | Part of Phase 5 refinement | “Finally, we close the loop — corrections, schema changes, and layout discoveries feed right back into the registry. Over time, this makes the framework self-learning. This is where the long-term ROI lies — smarter automation with every cycle.”