## Sheet1
WBS ID | Epic | Story Title | Description | Owner | Story Points | Complexity | Dependencies | Status | Comments
1.1 | Architecture & Design | Define MVP Scope | Define clear MVP boundaries, in-scope/out-of-scope items, and business KPIs. Acceptance Criteria: -Architecture presented as a diagram and document -Includes V1 pipeline, Registry, KNN, HITL -Includes cost optimization + scalability design -Reviewed by Helios and TFS (Yash) Deliverables: Master Architecture Design Doc | Sajid | 2 | S | — | Completed
1.2 | Architecture & Design | Document v2.0 Dataflow | Update architecture diagrams (Old vs New), address 4 reviewer concerns. | Sajid | 3 | M | 1.1 | Completed
1.3 | Architecture & Design | Define Registry Data Model |  | Sajid | 3 | M | 1.1 |  | Helios can mock schema locally and refine later so it does not block our progress.
1.4 | Architecture & Design | Define Tiered Classification Rules | Define the logic for Tier 1 (high confidence), Tier 2 (medium), and Tier 3 (default). Specify thresholds, confidence checks, and cluster consensus logic. Acceptance Criteria: -Tier 1/2/3 clearly documented -DEFAULT fallback defined -Cluster separation rule defined -Shared with Helios for implementation | Sajid | 3 | M | 1.1 |  | Helios codes rules parametrically; exact values can be tuned later.
1.5 | Architecture & Design | Define HITL Workflow | Document roles, audit fields, promote-to-registry logic. | Sajid | 2 | S | 1.1 |  | HITL is Phase-2; does not block core registry coding.
2.1 | Infra | Provision Postgres (Dev) | Set up managed Postgres instance for Registry. | TFS | 3 | M | 1.3 |  | Helios can work locally with Docker Postgres.
2.2 | Infra | Enable pgvector + IVFFlat | Enable extensions for vector search. | TFS | 3 | M | 2.1 |  | Local clone supports these extensions.
2.3 | Infra | Configure Network + Secrets | Set up secure connectivity and secrets. | TFS | 3 | M | 2.1 |  | Only needed before deployment; not needed for local dev.
2.4 | Infra | Grant DB Access Provide Dev Credentials | Grant access to Sajid + Helios. | TFS | 2 | S | 2.1 |  | Helios can use local DB until real access is granted.
3.2 | Registry | Fingerprinting Engine | Generate SHA-based layout fingerprints. | Helios | 3 | M | 1.3 |  | Schema only; exact fields can evolve.
3.3 | Registry | Registry DB Integration | Implement CRUD for layouts table. | Helios | 5 | M | 3.2 |  | Uses local Postgres; Infra DB not needed yet.
3.4 | Registry | KNN Search via pgvector | Implement vector similarity search. | Helios | 5 | M | 3.3 |  | Can test locally with seeded data.
3.5 | Registry | /match API | Expose API for layout matching. | Helios | 5 | M | 3.2, 3.4 |  | Integrates fingerprint + KNN; no Infra dependency.
3.6 | Registry | /promote API | Promote HITL-reviewed layouts to registry. | Helios | 5 | M | 3.5 |  | HITL is Phase-2; API can be stubbed earlier.
3.7 | Registry | Seed Initial Layouts | Load sample AE forms and embeddings. | Helios | 3 | M | 3.3 |  | Needed for integration test only; not coding-blocking.
4.1 | Embeddings | Hybrid Feature Generator | Extract text + geometric features. | Helios | 5 | M | 1.3 |  | You define structure; implementation is independent of Infra.
4.2 | Embeddings | Embedding Model Integration | Convert hybrid features to vectors. | Helios | 5 | M | 4.1 |  | Embedding code can run locally; no Infra required.
4.3 | Embeddings | Tiered Classification Engine | Implement Tier 1/2/3 logic with DEFAULT fallback. | Helios | 5 | L | 1.4, 4.2 |  | Uses configurable thresholds; doesn’t need final tuning.
4.4 | Embeddings | Logging + Metrics | Track match confidence, tiers, fallback stats. | Helios | 3 | M | 4.3 |  | Logging is internal to app; not dependent on DB infra.
5.2 | HITL | Web App → /match Integration | Call Registry /match API from PV app. | Helios | 5 | M | 3.5 |  | Web app can use mock data until backend ready.
5.3 | HITL | Accept & Promote Integration | Call /promote API to update registry. | Helios | 5 | M | 3.6 |  | Can integrate after registry API is functional.